## Greater Lincolnshire Public Service Compact Action Plan 2018 (signed off)

| Core Objective | What will be done (Action) | By whom | Outcomes / Indicators | Timescales | Sign off statement |
| --- | --- | --- | --- | --- | --- |
| To work with GLLEP to support the implementation of their skills strategy | A Greater Lincolnshire Local Enterprise Partnership (GLLEP) representative to formally report progress to the Steering Group meetings throughout 2018 | Compact Steering Group and representative from GLLEP | An identifiable link in place between the Lincs Compact and GLLEP to address skills development in Greater Lincolnshire | Throughout 2018 | Reports received at each quarterly Steering Group meeting. GLLEP and Compact now working together |
| To promote working in public service as a career of choice | Public Service Apprentices to present at the Feb 18 Apprenticeships event Task & Finish group established (at March Steering Group meeting) to establish a sub action plan to agree outcomes and actions Support the development of attraction strategies for specialist occupations Identify and support young people in public service to promote this sector as a career of choice | Compact Steering Group and young public sector workers | To be decided at the March Steering Group meeting | February 2018 March 2018 Throughout 2018 Throughout 2018 | PS Apprentices gave the keynote address at Feb event Attraction Strategies event delivered in May. All materials available of Compact web site |
| To promote and develop Apprentice schemes in Greater Lincolnshire (raise the profile of Apprenticeship occupations in the public sector) | Increase the number of Apprentices working in the Public Service in Greater Lincolnshire Public Service Apprentice of the Year award to be presented | Member organisations of the Lincs PS Compact | The number of Apprentices to be increased by a % amount decided at the March 2018 Steering Group meeting PS Apprentice of the Year identified and rewarded | December 2018 August 2018 | In January 2018 a survey taken of member orgs to identify the number of Apps working in member orgs. To be refreshed in Jan 2019 to observe change PS AotY Awards presented in Nov |
| To promote and develop Apprentice schemes in Greater Lincolnshire (share knowledge of Apprenticeship developments within the network) | Share knowledge of Apprenticeship developments within the Compact network through: Good Practice Event in February 2018 Reports at each Steering Group meeting by East Midlands Apprenticeships Ambassador | Facilitator Apprenticeship Ambassador | Apprenticeships event delivered Reports received and published | February 2018 December 2018 | Apps Where are We Now event delivered in Feb Apps CoP Group established and best practice materials produced and distributed via Compact web site |
| Sharing good practice | Sharing good practice | Facilitator with support from all Steering Group members | 4 good practice events delivered in 2018 to address issues of common concern and interest for Compact member organisations. | February 2018 May 2018 August 2018 November 2018 | 4 events delivered: Apps (Feb); Attraction Strategies (May); Working with Academia (Aug) and Celebrating and Planning (Nov) |
| To promote improved access to training and funding for training | Promote shared awareness and facilitate improved access to training and funding for training | A Compact Steering Group member from the FE community | At each Steering Group meeting current information relating to improved access to training and funding for training | Ongoing | FE representative to formally reported progress to the Steering Group at all meetings |

| Additional Enabling Objective | What will be done (Action) | By whom | Outcomes / Indicators | Timescales | Comments / Monitoring & Reporting |
| --- | --- | --- | --- | --- | --- |
| Liaise effectively with the third sector to promote a coordinated approach to the delivery of public services | A third sector representative to identify opportunities at all Steering Group meetings in 2018 | Compact Steering Group and representation from the Third Sector | Current relevant information relating to opportunities for the third sector and the public sector to work together effectively in Lincs made available to all Compact member organisations | Throughout 2018 | A third sector representative to identified opportunities at all Steering Group meetings in 2018 |
| Liaise effectively with trade unions and staff associations to support education and training at work | Specific action to be agreed at March Steering Group |  |  |  | Info about the UNISON Get on at Work scheme disseminated. ULHT are going to take part in 2019. |
| Raise the profile of the Compact as a vehicle for delivery of the wider skills agenda | Gather info on skills gaps and then work with organisations to support recruitment | Facilitator with support from all Steering Group members | Identifiable partnerships in place | Gathering by March 18. Collaborative work planned March 2018 implemented by December 2018 |  |
| Consult with member organisations to plan activity for 2019 | Undertake a survey of member organisation | Facilitator | 2019 action plan informed by member organisations | Autumn 2018 for consideration by Steering Group in December 2018 | Three planning sessions for 2019 took place in Nov and Dec (At the Planning event in Nov, at SG in DC and via email late Dec) |