## Lincs Public Service Compact Action Plan for ‘All things Apprenticeships’ – updated after May meeting

| Ref | What will be done (Action) | By whom | Outcomes | Timescales | Comments / Monitoring & Reporting | Comments | Updated after May 2018 Community of Practice meeting |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Establish a Community of Practice (CoP) to facilitate networking and collaborative working to address issues of common concern relating to the Apprenticeships agenda | Facilitated by Chris Donkin and contributions from members of the CoP | CoP to meet quarterly prior to each Steering Group meeting | May 2018 Aug 2018 Nov 2018 | The CoP will report to the Steering Group who will provide an additional ‘steer’ for activity to be pursued by the CoP | The agenda for CoP meetings to be set by the group. Issues to be discussed / addressed will vary from meeting to meeting | CoP now established – meeting taken place in May 18 (see minutes) and date of Aug meeting set |
| 2 | Promote and develop Apprentice schemes in Greater Lincolnshire (share knowledge of Apprenticeship developments) | Mike Johnson | Reports at each CoP meeting by East Midlands Apprenticeships Ambassador | May 2018 Aug 2018 Nov 2018 | Copies of the Ambassadors report will be provided to each SG meeting | The intention is that this activity will help to contribute to an increase in the number of Apprentices working in public service in Lincs. | First update from Mike given at the May CoP meeting (see minutes) |
| 3 | 20% off the job log and plan to be developed | Produced initially by Chris Donkin and Pauline Mould. Then distributed for comment and revisions from other CoP members | An e-version of a credible Log and a credible plan to be produced and available for use by other Compact members | By end of May 2018 |  | Drafts of the log and the plan to be made available. Initially Chris Donkin and Pauline Mould to produce the drafts. | Complete set of resources for 20% OTJ produced and available from web site: (i) OTJ recording template (ii) OTJ planning s-sheet (iii) AELP guidance for OTJ eligible activities and (iv) Grantham College pp and case study |
| 4 | Re-fresh of survey of member orgs to check on how many Apps are employed (to monitor subsequent increase) | Chris Donkin to administer the survey | Survey results available for consideration by Steering Group and for reference to the CoP | By end of May 2018 |  | The re-fresh to also include a breakdown of Apprenticeships by level | re-fresh to include breakdown of Apprenticeships by level to be completed by end of May and be made available to the Compact SG in June |
| 5 | The Compact to present a ‘Public Service App of the Year’ award | Chris Donkin with help from colleagues from the Compact Steering Group (see also ‘Comments’) | The award to be presented at the Compact Sept good practice event (likely to be themed around ‘Attraction Strategies’) | Award to be presented in Sept | Formal evaluation of this activity to be undertaken and considered by CoP at their Nov 18 gathering | Paul Collins to source possible sponsorship from the Federation of Lincolnshire Colleges. | Sub group established to progress this issue and deliver the ‘PS App of the Year’ awards by September |
| 6 | The CoP to ensure that the materials developed by the Community are disseminated to the Compact membership | Chris Donkin with help from colleagues from the CoP | Materials emailed out to ‘key contacts’ and made available on the Compact web site | May 2018 Aug 2018 Nov 2018 | Subsequent CoP meetings to record impact of materials being distributed / used | Materials / examples of good practice to also be disseminated at Steering Group meetings | Approach agreed at May 2018 CoP meeting (see minutes) |