## Greater Lincolnshire Public Service Compact Action Plan for 2018: Updated June 2018

| Core Objective | What will be done (Action) | By whom | Outcomes / Indicators | Timescales | Updated following March 2018 SG meeting | Updated after June 2018 SG meet |
| --- | --- | --- | --- | --- | --- | --- |
| To work with GLLEP to support the implementation of their skills strategy | A Greater Lincolnshire Local Enterprise Partnership (GLLEP) representative to formally report progress to the Steering Group meetings throughout 2018 | Compact Steering Group and representative from GLLEP | An identifiable link in place between the Lincs Compact and GLLEP to address skills development in Greater Lincolnshire | Throughout 2018 | Update given by Clare Hughes of the GLLEP at the Mar SG meeting (see minutes) | No update given at June 2018 meeting. Next update scheduled for Sept 2018 SG meeting |
| To promote working in public service as a career of choice | Public Service Apprentices to present at the Feb 18 Apprenticeships event Task & Finish group established (at March Steering Group meeting) to establish a sub action plan to agree outcomes and actions Support the development of attraction strategies for specialist occupations Identify and support young people in public service to promote this sector as a career of choice | Compact Steering Group and young public sector workers | To be decided at the March Steering Group meeting | February 2018 March 2018 Throughout 2018 Throughout 2018 | Achieved – see minutes of Mar SG meet Group established at SG meet. First gathering (to produce Action Plan) scheduled for early April Mooted that third (Aug) good practice event will be themed on ‘Attraction strategies Task and Finish Group for promoting the PS established at SG meet. First gathering (to produce Action Plan) scheduled for early April | Apps Community of Practice (CoP) now established and has met twice. CoP is addressing issues of concern and interest relating to the Apps agenda locally. CoP Action Plan available on Compact web site. Promo of PS Working Group established (Group’s Action Plan on web site) and group is supporting ‘Attraction Strategies event in Sept |
| To promote and develop Apprentice schemes in Greater Lincolnshire (raise the profile of Apprenticeship occupations in the public sector) | Increase the number of Apprentices working in the Public Service in Greater Lincolnshire Public Service Apprentice of the Year award to be presented | Member organisations of the Lincs PS Compact | The number of Apprentices to be increased by a % amount decided at the March 2018 Steering Group meeting PS Apprentice of the Year identified and rewarded | December 2018 August 2018 | In January 2018 a survey taken of member orgs to identify the number of Apps working in member orgs. Outline target for 2018 agreed at Mar SG meet. Progress towards target to be reported at each Steering Group meeting in 2018. | Consideration of Apps survey data at June SG meeting (see minutes) |
| To promote and develop Apprentice schemes in Greater Lincolnshire (share knowledge of Apprenticeship developments within the network) | Share knowledge of Apprenticeship developments within the Compact network through: Good Practice Event in February 2018 Reports at each Steering Group meeting by East Midlands Apprenticeships Ambassador | Facilitator Apprenticeship Ambassador | Apprenticeships event delivered Reports received and published | February 2018 December 2018 | Event delivered and evaluated (see Mar 18 SG minutes) Report provided at Mar 18 SG meeting (see minutes) | Reports of national and local Apprenticeships developments now scheduled for Apps CoP (rather than SG). Reports available from CoP minutes |
| Sharing good practice | Sharing good practice | Facilitator with support from all Steering Group members | 4 good practice events delivered in 2018 to address issues of common concern and interest for Compact member organisations. | February 2018 May 2018 August 2018 November 2018 | Feb 18 Apprenticeships event delivered May 18 (Unis event) planned Aug Event (Attraction strategies planned | May (Working with Academia) event delivered. Sept attraction strategies event now in planning phase |
| To promote improved access to training and funding for training | Promote shared awareness and facilitate improved access to training and funding for training | A Compact Steering Group member from the FE community | At each Steering Group meeting current information relating to improved access to training and funding for training | Ongoing | Information relating to the future of ESF funding disseminated by GLLEP rep at the Mar SG meeting (see minutes) | No further update given at June 2018 meeting. Next update scheduled for Sept 2018 SG meeting |

| Additional Enabling Objective | What will be done (Action) | By whom | Outcomes / Indicators | Timescales | Updated following March 2018 SG meeting | Update following June 2018 SG meeting |
| --- | --- | --- | --- | --- | --- | --- |
| Liaise effectively with the third sector to promote a coordinated approach to the delivery of public services | A third sector representative to identify opportunities at all Steering Group meetings in 2018 | Compact Steering Group and representation from the Third Sector | Current relevant information relating to opportunities for the third sector and the public sector to work together effectively in Lincs made available to all Compact member organisations | Throughout 2018 | Current relevant information relating to opportunities for the third sector and the public sector to work together effectively in Lincs made available to Compact member organisations by third sector reps at the Mar 2018 SG meeting (see minutes) | Current relevant information relating to opportunities for the third sector and the public sector to work together effectively in Lincs made available to Compact member organisations by Rachel Aylmer of Childrens Links at the June 2018 SG meeting (see minutes) |
| Liaise effectively with trade unions and staff associations to support education and training at work | Specific action to be agreed at March Steering Group |  |  |  | Actions deferred until the facilitator has had the opportunity to speak to reps from UNISON and GMB to establish best way of working with the unions to support education and training at work | Information about the UNISON Get on at Work scheme disseminated at the June SG minutes – see minutes and also copy of the presentation available for download from the web site |
| Raise the profile of the Compact as a vehicle for delivery of the wider skills agenda | Gather info on skills gaps and then work with organisations to support recruitment | Facilitator with support from all Steering Group members | Identifiable partnerships in place | Gathering by March 18. Collaborative work planned March 2018 implemented by December 2018 | Actions deferred. The implementation of this action will be advised by the work of the ‘Promoting the public sector’ task and finish group reports back | The ‘Promoting the public sector’ task and finish group has an Action Plan (available on web site) including (i) working with schools and (ii) supporting development of effective attraction strategies. |
| Consult with member organisations to plan activity for 2019 | Undertake a survey of member organisation | Facilitator | 2019 action plan informed by member organisations | Autumn 2018 for consideration by Steering Group in December 2018 | Design of the survey to be considered at June 2018 Steering Group | Action deferred until Sept 2018 meeting. |